## Project Plan Template
PROJECT PLAN TEMPLATE
| PROJECT TITLE |  | START DATE
| IceMetrics |  | 2025-02-03 |  |  | PROJECT DURATION
| PROJECT MANAGERS |  | END DATE |  |  | in days
| Jake Morgan and Tin Doung |  | 2025-05-10 |  |  | 97
TASK NO. | TASK NAME | STATUS | ASSIGNED TO | START DATE | END DATE | DURATION in days | COMMENTS | STATUS
1 | PLANNING AND SETUP | Complete |  | 2025-02-03 | 2025-02-11 | 9 |  | Not Started
1.1 | Initialize Repository | Complete | Tin | 2025-02-03 | 2025-02-05 | 3 | Repository set up and cloned on both machines | In Progress
1.2 | Setup Development Environment (React, Material UI, FastAPI) | Complete | Jake / Tin | 2025-02-03 | 2025-02-05 | 3 | Set up and install framework locally and test run | Complete
1.3 | Create Landing Page | Complete | Jake | 2025-02-06 | 2025-02-10 | 5 | The landing page design and layout | On Hold
1.4 | Create Sign In and Sign Up pages | Complete | Jake | 2025-02-06 | 2025-02-10 | 5 | Sign in page design and layout
1.5 | Create the initial database schema | Complete | Tin | 2025-02-08 | 2025-02-09 | 2 | Database schema for database
1.6 | Setup a connection between front, back, and database | Complete | Jake / Tin | 2025-02-09 | 2025-02-11 | 3 | Connect the front end test requests with the bakend and database to ensure everything runs without problems initially
2 | WEB APP CREATION | In Progress |  | 2025-02-11 | 2025-04-08 | 57
2.1 | User Authentication System | In Progress | Jake/Tin | 2025-02-11 | 2025-04-08 | 57 | Implement login/logout, session management, and authentication with JWT tokens.
2.2 | User Dashboard | In Progress | Jake | 2025-02-11 | 2025-04-08 | 57 | Develop a dashboard for users to view their hockey analytics, including game statistics, player tracking, and performance metrics.
2.3 | UI Styling & Optimization | In Progress | Jake | 2025-02-13 | 2025-04-08 | 55 | Refine CSS, add Material UI components, and optimize responsiveness for different screen sizes.
2.4 | Video Upload & Management System | In Progress | Jake | 2025-02-17 | 2025-04-08 | 51 | Implement a user-friendly interface for uploading hockey game footage, storing metadata, and integrating it with OpenCV processing.
3 | OPENCV VIDEO ANALYSIS | Complete |  | 2025-02-03 | 2025-04-08 | 65
3.1 | Set I/O functions for OpenCV | In Progress | Tin | 2025-02-11 | 2025-04-08 | 57 | OpenCV functions for data processing from user->system
3.2 | Video/ frame processing functions (video -> NumPy Array) | In Progress | Tin | 2025-02-11 | 2025-04-08 | 57 | Breaking the video input from user or database into numpy arrays to manipulate the pixels to apply tracking,etc.
3.2.1 | Create video statistics and information functions for analysis | In Progress | Jake/Tin | 2025-02-07 | 2025-04-08 | 61 | This will be functions that uses libraries to calculate statistics of the video and provide feedback
3.2.2 | Connect video output and statistics onto database | Not Started | Jake/Tin | 2025-02-03 | 2025-04-08 | 65
3.3 | Database retrieval / display of stats into Material UI front end view | Not Started | Jake | 2025-02-03 | 2025-04-08 | 65 | Use the data from the statistics which is stored on database to display per video id that is linked with user
3.3.1 | Test front end , backend and database to ensure data integrity | In Progress | Jake/Tin | 2025-02-03 | 2025-04-08 | 65 | This step is to make sure that there is nothing wrong with the implemetation with OpenCV integration
3 | PRESENTATION | Not Started |  | 2025-04-08 | 2025-05-10 | 33
3.1 | – Class Presentation | Not Started | Jake / Tin | 2025-04-08 | 2025-05-10 | 33
3.2 | – (Possible) Board Presentation | Not Started | Jake / Tin | 2025-04-08 | 2025-05-10 | 33
3.3 | – (Possible) CS1050 Presentation | Not Started | Jake / Tin | 2025-04-08 | 2025-05-10 | 33

## BLANK - Project Plan Template
PROJECT PLAN TEMPLATE
| PROJECT TITLE |  | START DATE
PROJECT DURATION
| PROJECT MANAGER |  |  |  |  | in days
1
WBS NO. | TASK NAME | STATUS | ASSIGNED TO | START DATE | END DATE | DURATION in days | COMMENTS | STATUS
1 | PROJECT CONCEPTION AND INITIATION |  |  |  |  | 1 |  | Not Started
1.1 | – Project Charter |  |  |  |  | 1 |  | In Progress
1.1.1 | –– Project Charter Revisions |  |  |  |  | 1 |  | Complete
1.2 | – Research |  |  |  |  | 1 |  | On Hold
1.3 | – Projections |  |  |  |  | 1
1.4 | – Stakeholders |  |  |  |  | 1
1.5 | – Guidelines |  |  |  |  | 1
1.6 | – Project Initiation |  |  |  |  | 1
2 | PROJECT DEFINITION AND PLANNING |  |  |  |  | 1
2.1 | – Scope & Goal Setting |  |  |  |  | 1
2.2 | – Budget |  |  |  |  | 1
2.3 | – Communication Plan |  |  |  |  | 1
2.4 | – Risk Management |  |  |  |  | 1
3 | PROJECT LAUNCH & EXECUTION |  |  |  |  | 1
3.1 | – Status & Tracking |  |  |  |  | 1
3.2 | – KPIs |  |  |  |  | 1
3.2.1 | –– Monitoring |  |  |  |  | 1
3.2.2 | –– Forecasts |  |  |  |  | 1
3.3 | – Project Updates |  |  |  |  | 1
3.3.1 | –– Chart Updates |  |  |  |  | 1
4 | PROJECT PERFORMANCE / MONITORING |  |  |  |  | 1
4.1 | – Project Objectives |  |  |  |  | 1
4.2 | – Quality Deliverables |  |  |  |  | 1
4.3 | – Effort & Cost Tracking |  |  |  |  | 1
4.4 | – Project Performance |  |  |  |  | 1
Double-click Horizontal (Value) Axis to format Bound Minimum and Bound Maximum settings under Axis Options.* Delete any unpopulated rows in your table.*

## -Disclaimer-
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.